## Milestones
MILESTONE | COLOR | DESCRIPTION
Research |  | We lack some knowledge required to implement our designs successfully. Therefore, researching such subjects before development is putting our best foot forward.
Sourcing |  | Several parts of our system require data from external sources. We must collect sources of such data, again, before development.
Front End |  | Knowball is a game. We need a front-end interface for players to interact with, making this one of our major, long-term deliverables.
Database |  | Our design demands a database to service the game and obscurity engine. Again, this is one of our major, long-term deliverables.
Obscurity Engine |  | The obscurity engine is, perhaps, the most important part of our system. It is the foundation of the idea that became Knowball. Without it, there is no game. This is our third major, long-term deliverable.
Validation |  | We must validate player guesses for correctness, and our prompts for reasonable challenge. There are several tasks to drive the development of such logic.
Presentation |  | Throughout the semester, we should steadily contribute to our final presentation. This is an essential determinant of our grade and performance at the expo.

## Timeline
TASK | LEAD | START | END | WEEK 0 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
Research
Research data-analysis libraries in Python to inform the most suitable choice for our Obscurity Engine. | Stetson |  | 2024-01-13 | bar: WEEK 0
Research front-end frameworks (Vue.js, React, Angular, etc.) to inform the most suitable choice. | Blair |  | 2024-01-13 | bar: WEEK 0
Research uses for ML in the Obscurity Engine to inform the most suitable choice for its potential inclusion. | Blair |  | 2024-01-13 | bar: WEEK 0
Research database frameworks (MySQL, PostgreSQL, MongoDB, SQLite, etc.) to inform the most suitable choice. | Ben |  | 2024-01-13 | bar: WEEK 0
Research platforms on which to host the database (Azure, AWS, etc.) to inform the most suitable choice. | Ben |  | 2024-01-13 | bar: WEEK 0
Sourcing
Collect parameters for the Obscurity Engine (i.e., relevant metrics the engine should compute over). | Blair |  | 2024-01-13 | bar: WEEK 0
Collect options for sport-statistics APIs and weigh them against the alternative of web scraping. | Ben | 2024-01-13 | 2024-01-20 | bar: WEEK 1
Guide discussion of weights on Obscurity Engine parameters (e.g., social following versus on-field statistics). | Stetson | 2024-01-13 | 2024-01-20 | bar: WEEK 1
Front End
Design the UI/UX with a sequence of mockups representing state transitions. | Blair | 2024-01-13 | 2024-01-20 | bar: WEEK 1
Develop the front end, per the mockups approved in the previous task, and vet it with test data. | Blair | 2024-02-03 | 2024-02-17 | bar: WEEK 4 to WEEK 5
Connect the front end to backend processes like the Query Manager, Guess Validator, Obscurity Engine, etc. | Blair | 2024-02-17 | 2024-02-24 | bar: WEEK 6
Database
Design the "Athlete DB" with Entity Relationship Diagrams. | Ben | 2024-01-20 | 2024-01-27 | bar: WEEK 2
Create database tables with the chosen framework, on the chosen platform. Populate them with test data. | Ben | 2024-01-27 | 2024-02-03 | bar: WEEK 3
Obscurity Engine
Create Obscurity Engine | Blair | 2024-01-20 | 2024-02-10 | bar: WEEK 2 to WEEK 4
Tune the Obscurity Engine based on its response to predetermined test cases. | Stetson | 2024-02-10 | 2024-02-24 | bar: WEEK 5 to WEEK 6
Tune standardization factors for our metrics across different countries, sports, leagues, etc. | Stetson | 2024-02-10 | 2024-02-24 | bar: WEEK 5 to WEEK 6
Tune the Score Converter to produce digestible outputs for players of our game. | Stetson | 2024-02-10 | 2024-02-24 | bar: WEEK 5 to WEEK 6
Validation
Decompose natural language questions into manageable logic for the Question Validator. | Blair | 2024-02-24 | 2024-03-10 | bar: WEEK 7 to WEEK 8
Refine the desired system operations during gameplay (i.e., the I/O through system components). | Ben | 2024-02-24 | 2024-03-03 | bar: WEEK 7
Tune the threshold of the Question Validator so that only questions of reasonable difficulty are pushed to the database. | Stetson | 2024-03-10 | 2024-03-17 | bar: WEEK 9
Presentation
Work on Final Presentation | Ben |  | 2024-03-24

## Effort Matrix
TASK | LEAD | BEN | BLAIR | STETSON
Research
Research data-analysis libraries in Python to inform the most suitable choice for our Obscurity Engine. | Stetson | 25% | 25% | 50%
Research front-end frameworks (Vue.js, React, Angular, etc.) to inform the most suitable choice. | Blair | 25% | 50% | 25%
Research uses for ML in the Obscurity Engine to inform the most suitable choice for its potential inclusion. | Blair | 25% | 50% | 25%
Research database frameworks (MySQL, PostgreSQL, MongoDB, SQLite, etc.) to inform the most suitable choice. | Ben | 50% | 25% | 25%
Research platforms on which to host the database (Azure, AWS, etc.) to inform the most suitable choice. | Ben | 50% | 25% | 25%
Sourcing
Collect parameters for the Obscurity Engine (i.e., relevant metrics the engine should compute over). | Blair | 25% | 50% | 25%
Collect options for sport-statistics APIs and weigh them against the alternative of web scraping. | Ben | 50% | 25% | 25%
Guide discussion of weights on Obscurity Engine parameters (e.g., social following versus on-field statistics). | Stetson | 25% | 25% | 50%
Front End
Design the UI/UX with a sequence of mockups representing state transitions. | Blair | 25% | 50% | 25%
Develop the front end, per the mockups approved in the previous task, and vet it with test data. | Blair | 25% | 50% | 25%
Connect the front end to backend processes like the Query Manager, Guess Validator, Obscurity Engine, etc. | Blair | 25% | 50% | 25%
Database
Design the "Athlete DB" with Entity Relationship Diagrams. | Ben | 50% | 25% | 25%
Create database tables with the chosen framework, on the chosen platform. Populate them with test data. | Ben | 50% | 25% | 25%
Obscurity Engine
Create Obscurity Engine | Blair | 25% | 50% | 25%
Tune the Obscurity Engine based on its response to predetermined test cases. | Stetson | 25% | 25% | 50%
Tune standardization factors for our metrics across different countries, sports, leagues, etc. | Stetson | 25% | 25% | 50%
Tune the Score Converter to produce digestible outputs for players of our game. | Stetson | 25% | 25% | 50%
Validation
Decompose natural language questions into manageable logic for the Question Validator. | Blair | 25% | 50% | 25%
Refine the desired system operations during gameplay (i.e., the I/O through system components). | Ben | 50% | 25% | 25%
Tune the threshold of the Question Validator so that only questions of reasonable difficulty are pushed to the database. | Stetson | 25% | 25% | 50%
Presentation
Work on Final Presentation | Ben | 50% | 25% | 25%